Receiver(s): Departments at the Faculty of Health, Faculty of Arts, Faculty of Natural Sciences, Faculty of Technical Sciences and School of Business and Social Sciences

ERC Consolidator Grant 2025

Links:	-

Consolidator Grant | ERC (europa.eu)

- ERC Dashboard – link to funded projects (filter for instrument/panel/year)

| Process plan |  |  |
| --- | --- | --- |
| Date | Task | Responsible |
| 16 August 2024 | Process information and timing Sending process plan and information to departments | Departments and Dean’s Offices at Health, ARTS, NAT, TECH and BSS Research Support Office, ERC team |
| 28 August 2024 | Overview of applicants A list of potential department applicants is sent to the Research Support Office: lgrau@au.dk Eligible applicants - researchers from any research field and of any nationality. - PhD age: > 7 and ≤ 12 years prior to 1 January 2025*. - scientific track record showing great promise. *[= Successful defence of PhD between 1 January 2013 and 31 December 2017 (inclusive)] | Departments and local scientific coordinators |
| 29 August 2024 | Assigning Research Support Staff Based on the list of possible applicants, the Research Support Office assigns RSO staff to assist in the application process. Individual application process and a possible start-up meeting is arranged between the applicant and the assigned research-funding advisor. | Research Support Office, ERC team Applicant and Research Support Office |
| 26 September 2024 | ERC CoG call opens Panel chairs are announced. | ERC Executive Agency |
| September - January 2024 | Supporting the applicant in the application process Support with all aspects of the application (feedback on B1 and B2, bibliometric analysis, etc.) - formalities (Part A), budget, Host Letter | Research Support Office, ERC team |
| Deadline – January 14 2025 |  |  |
| (indicative) July 2025 | Invitations for interviews | ERC Executive Agency |
| (indicative) October 2025 | Mock interviews Those applicants who are invited to the interview phase will get an opportunity to present their project in a setting resembling the official online ERC interview. Panel: - Former ERC grantees - Scientific peers - Research Support Office staff | Research Support Office, ERC team |
| (indicative) October 2025 | Step 2 Interviews | ERC Executive Agency Applicant |
| (indicative) December 2025 | Evaluation result – phase 2 Rejection or approval of grant | ERC Executive Agency |