|  |
| --- |
| Receiver(s): Departments at the Faculty of Health, Faculty of Arts, Faculty of Natural Sciences, Faculty of Technical Sciences and School of Business and Social Sciences |
|  |

ERC Consolidator Grant 2025

Links: -

[[Consolidator Grant | ERC (europa.eu)](https://erc.europa.eu/funding/starting-grants)](https://erc.europa.eu/apply-grant/consolidator-grant)

- [ERC Dashboard – link to funded projects (filter for instrument/panel/year)](https://dashboard.tech.ec.europa.eu/qs_digit_dashboard_mt/public/sense/app/c140622a-87e0-412e-8b29-9b5ddd857e13/sheet/61a0bd1d-cd6d-4ac8-8b55-80d8661e44c0/state/analysis)

|  |  |  |
| --- | --- | --- |
| **Process plan** | | |
| **Date** | **Task** | **Responsible** |
| **16**  **August**  **2024** | *Process information and timing*  Sending process plan and information to departments | Departments and Dean’s Offices at Health, ARTS, NAT, TECH and BSS  Research Support Office, ERC team |
| **28**  **August**  **2024** | *Overview of applicants*  A list of potential department applicants is sent to the Research Support Office: [lgrau@au.dk](mailto:lgrau@au.dk)    *Eligible applicants*   * researchers from any research field and of any nationality. * PhD age: > 7 and ≤ 12 years prior to 1 January 2025\*. * scientific track record showing great promise.   \*[= Successful defence of PhD between 1 January 2013 and 31 December 2017 (inclusive)] | Departments and local scientific coordinators |
| **29**  **August**  **2024** | *Assigning Research Support Staff*  Based on the list of possible applicants, the Research Support Office assigns RSO staff to assist in the application process.  Individual application process and a possible start-up meeting is arranged between the applicant and the assigned research-funding advisor. | Research Support Office, ERC team  Applicant and Research Support Office |
| **26**  **September**  **2024** | *ERC CoG call opens*  Panel chairs are announced. | ERC Executive Agency |
| **September -**  **January**  **2024** | *Supporting the applicant in the application process*  Support with all aspects of the application (feedback on B1 and B2, bibliometric analysis, etc.)  - formalities (Part A), budget, Host Letter | Research Support Office, ERC team |
| **Deadline – January 14 2025** | | |
| **(indicative)**  **July**  **2025** | *Invitations for interviews* | ERC Executive Agency |
| **(indicative)**  **October**  **2025** | *Mock interviews*  Those applicants who are invited to the interview phase will get an opportunity to present their project in a setting resembling the official online ERC interview.  Panel:  - Former ERC grantees  - Scientific peers  - Research Support Office staff | Research Support Office, ERC team |
| **(indicative)**  **October**  **2025** | *Step 2 Interviews* | ERC Executive Agency  Applicant |
| **(indicative)**  **December**  **2025** | *Evaluation result – phase 2*  Rejection or approval of grant | ERC Executive Agency |

